## Sheet1
Question # | Asked by | Question | Answer (by)
1 | Jerry Folger, Stratford Building | Is the target budget ($130-$160/sq. ft.) inclusive of foundations, utility hookups, and set and finish of the modules? | The square footage cost target does not include foundations or utilities to the buildings. But it does include hookup to the utilities and setting and finishing the modules. (Ginger)
2 | Matt Munther, Simplicity Homes (Hayden Homes) | Would we consider site-built products? SH does not do manufactured but could offer affordable site-built homes. | To remain consistent with the RFP and the Housing Authority’s procurement policy, we’re restricting ourselves to modular housing. (Lona)
3 | David Reddy (360 Analytics) | Passive House and Net-Zero have slightly different requirements. Do you envision a) doing an initial feasibility assessment to choose the path (PH or net-zero), and then once the path is determined, focus modeling/design optimization on this one path -or- b) are you interested evaluating/modeling against both metrics throughout the schematic design process? | Our experience is limited and we are hoping a consultant will guide us to the best approach. From the experience with HYC it seems likely we could achieve net zero on the Kennewick project given the size and location of the units. This is a small project, and although the state may cover the additional construction and A & E costs associated with UHEE, we want to be judicious about the cost of exploration of the concept and the cost of certification. (Ginger)
4 | Leo Perales (MTI) | Will this project be interested in receiving bids to perform any special inspections for site grading, concrete, asphalt pavement? Has this project gotten bids to perform a limited geotechnical investigation? | We are in the process of selecting a civil engineer. Once we have an engineer, we will determine what testing is needed for the project. (Stephen)
5 | Mike Goodwin (Cabin Creek Electric) | (1) Are these pre-manufactured modular homes that are already wired at the factory? If so, we would just need to bid the powering up of these homes? (2) I see the location in the specs, but it has nothing as far as what utility power is available. How are we powering all of these homes up? And (3) Will there be any electrical drawings available, or is this a plan/build type of project where we tell you what needs to be done to make these work? Lastly (4) In regards to the GC’s, are they just setting/installing the pre-manufactured homes? So any electrical work that needs to be done gets bid to them? | We are currently accepting proposals from energy consultants and modular manufacturers. We are not yet selecting general contractors or their subcontractors. Typically, the GC will bid out the project to subs in the case of site-built projects, so in this case, the site work will be bid out. The modular manufacturer will do their own electrical work for the buildings themselves. (Stephen)
6 | Pete Gombert (IndieDwell) | We are not yet licensed to operate in Washington State. This is not a long process and would be easy to accomplish by 2020, but given that it is a requirement of the project I wanted to confirm that would be acceptable. | RFP now reads, "License and ability to transport and install structures to a site in Washington State, or ability to subcontract transportation and installation to a subcontractor licensed in Washington State." (Lona, Ginger)
7 | Pete Gombert (IndieDwell) | 2. We do not have any availability on the 26th. Are there other dates we can meet with you and your team? | RFP now reads, "The ability for a representative from you firm to meet after 9:30 am on June 26th, 2019 or after 1:30 pm on June 27th, 2019 for an interview in Kennewick. For firms applying for only the energy modeling scope, an interview by telephone rather than in person is acceptable and will be scheduled by request on the dates and times reserved for interviews." (Lona, Ginger)
8 | David Reddy (360 Analytics) | Confirming that budgets are not required as part of the RFP response | Correct. Budgets are not required as part of RFP response (Adam)
9 | Carriage Houses NW | What is included in the cost/SF that was included in the RFP? | The cost/SF quoted in the RFP is for modular buildings delivered and installed on-site, not including the cost of site work or foundations. (Stephen)